## Test Plan
TEST PLAN
Project Name: | UI + API Hybrid Automation – ExpandTesting Notes App
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | Chikka Lokesh Prasad
Approved By: | QA Lead
SCOPE
Features to be Tested:
1 | UI Login functionality using valid and invalid credentials.
2 | UI Login functionality using valid and invalid credentials.
3 | Validate UI and API synchronization for created and deleted notes.
4 | Validate DOM updates without page refresh.
5 | Validate API response status codes and response time.
6 | Validate negative scenarios for UI and API modules.
TESTING TYPE
Functional Testing | ☑
Regression Testing | ☑
Integration Testing | ☑
UAT | ☐
TEST ENVIRONMENT
Environment: | QA
Browser/OS: | Google Chrome / Windows 11
TIMELINE
Start Date: | 2026-05-06
End Date: | 2026-05-08
RESOURCES
QA Lead: | Lokesh Prasad
QA Resources: | Selenium Python Automation Framework
Test Data Provider: | ExpandTesting Notes Application
RISKS & ASSUMPTIONS
Risks: | 1. Application instability may affect automation execution.
2. Network delays may impact API response timings.
3. Dynamic UI elements may cause flaky Selenium execution.
4. Test environment downtime may interrupt execution.
Assumptions: | 1. Test environment remains accessible during execution.
2. Valid test credentials are available.
3. API endpoints remain stable during testing.
4. Chrome browser and required drivers are installed properly.

## Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
TS-001 | Valid User Login | Validate login using valid email and password credentials | User account should be registered
TS-002 | Invalid User Login | Validate error message for invalid credentials | Login page should be accessible
TS-003 | Empty Login Validation | Validate login is blocked when fields are empty | User is on login page
TS-004 | Create Note via UI | Validate user can create note using category, title and description | User logged into Notes application
TS-005 | Instant DOM Update | Validate created note appears instantly without refresh | Note successfully created
TS-006 | Multiple Note Creation | Validate multiple notes appear correctly in notes list | User logged into Notes dashboard
TS-007 | GET Notes API Validation | Validate GET /notes API returns notes list successfully | API authentication token available
TS-008 | Create Note via API | Validate note creation using POST /notes API | User authenticated through API
TS-009 | Delete Note via API | Validate note deletion using DELETE /notes/{id} | Note exists in database
TS-010 | UI to API Validation | Validate note created in UI appears in API response | Note created successfully through UI
TS-011 | API to UI Synchronization | Validate deleted API note disappears from UI | Existing note available
TS-012 | API Response Time Validation | Validate API response time is below 2 seconds | API server available
TS-013 | Invalid API Request Validation | Validate API handles invalid requests properly | Invalid request payload prepared
TS-014 | Delete Note from UI | Validate user can delete note using UI delete flow | Existing note present in UI

## Test Cases
Test Case ID | Scenario ID | Test Case Name | Pre-conditions | Test Steps | Expected Result | Priority | Status
TC-UI-001 | TS-001 | Login with valid credentials | Login page opened | 1. Enter valid email 2. Enter valid password 3. Click Login button | User redirected to Notes dashboard successfully | High | Not Started
TC-UI-002 | TS-002 | Login with invalid credentials | Login page opened | 1. Enter invalid email/password 2. Click Login | Error message displayed | High | Not Started
TC-UI-003 | TS-003 | Login with empty fields | Login page opened | 1. Leave email empty 2. Leave password empty 3. Click Login | User should remain on login page | Medium | Not Started
TC-UI-004 | TS-004 | Create note using UI | User logged into Notes dashboard | 1. Click Add Note 2. Select category 3. Enter title 4. Enter description 5. Click Save | Note created successfully and visible in UI | High | Not Started
TC-UI-005 | TS-005 | Validate DOM update without refresh | Note created successfully | 1. Create new note 2. Observe notes list without refreshing page | Newly created note appears instantly in UI | High | Not Started
TC-UI-006 | TS-006 | Create multiple notes | User logged into dashboard | 1. Create first note 2. Create second note 3. Create third note | All notes displayed correctly in notes list | Medium | Not Started
TC-UI-007 | TS-014 | Delete note using UI | Existing note available | 1. Click Delete button 2. Click Confirm Delete | Note removed from UI successfully | High | Not Started
TC-API-001 | TS-007 | Validate GET /notes API | API authentication completed | 1. Send GET /notes request | API returns 200 response with notes list | High | Not Started
TC-API-002 | TS-008 | Create note using API | User authenticated through API | 1. Send POST /notes request with payload | New note created successfully | High | Not Started
TC-API-003 | TS-009 | Delete note using API | Existing note ID available | 1. Send DELETE /notes/{id} request | Note deleted successfully | High | Not Started
TC-API-004 | TS-012 | Validate API response time | API endpoint available | 1. Send GET /notes request 2. Measure response time | Response time should be below 2 seconds | Medium | Not Started
TC-API-005 | TS-013 | Create note with empty title | API authentication completed | 1. Send POST request with empty title | Validation error returned | Medium | Not Started
TC-E2E-001 | TS-010 | Validate UI-created note in API | User logged into UI and API | 1. Create note using UI 2. Call GET /notes API 3. Compare note details | UI note data should match API response | High | Not Started
TC-E2E-002 | TS-011 | Validate API delete reflected in UI | Existing note available | 1. Delete note using API 2. Refresh UI 3. Check notes list | Deleted note should disappear from UI | High | Not Started

## Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid Login Credentials | Email:chikkalokeshprasad04@gmail.com Password:Lokesh@123 | Used for successful login validation
TD-002 | Invalid Login Credentials | Email: invalid@test.com Password: WrongPass123 | Used for negative login testing
TD-003 | Empty Login Data | Email: Empty Password: Empty | Used for empty field validation
TD-004 | Valid Note Data | Category: Home Title: UI Test Note Description: Created using Selenium automation | Used for UI note creation testing
TD-005 | Multiple Notes Data | Note 1: Work Task Note 2: Personal Reminder Note 3: API Validation Note | Used for multiple note creation testing
TD-006 | API Create Note Payload | { "title":"API Note", "description":"Created from API", "category":"Home" } | Used for POST /notes API validation
TD-007 | Invalid API Payload | { "title":"", "description":"Invalid data" } | Used for API negative testing
TD-008 | Delete Note Test Data | Existing Note ID from GET /notes response | Used for DELETE /notes/{id} API validation
TD-009 | E2E Validation Data | Same note title and description for UI and API comparison | Used for UI to API synchronization testing
TD-010 | Performance Test Data | GET /notes API response time below 2 seconds | Used for API performance validation

## Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-UI-001 | Cycle-1 | Login with valid credentials | Lokesh Prasad | 2026-05-06 | Pass | - | User redirected to Notes dashboard successfully
TC-UI-002 | Cycle-1 | Login with invalid credentials | Lokesh Prasad | 2026-05-06 | Pass | - | Proper error message displayed
TC-UI-003 | Cycle-1 | Login with empty fields | Lokesh Prasad | 2026-05-06 | Pass | - | Login blocked successfully
TC-UI-004 | Cycle-1 | Create note using UI | Lokesh Prasad | 2026-05-06 | Pass | - | Note created and visible in UI
TC-UI-005 | Cycle-1 | Validate DOM update without refresh | Lokesh Prasad | 2026-05-06 | Pass | - | Note visible instantly without reload
TC-UI-006 | Cycle-1 | Create multiple notes | Lokesh Prasad | 2026-05-06 | Pass | - | All notes displayed correctly
TC-UI-007 | Cycle-1 | Delete note using UI | Lokesh Prasad | 2026-05-06 | Pass | - | Note deleted successfully
TC-API-001 | Cycle-1 | Validate GET /notes API | Lokesh Prasad | 2026-05-06 | Pass | - | API returned 200 response
TC-API-002 | Cycle-1 | Create note using API | Lokesh Prasad | 2026-05-06 | Pass | - | Note created through API
TC-API-003 | Cycle-1 | Delete note using API | Lokesh Prasad | 2026-05-06 | Pass | - | Note deleted successfully
TC-API-004 | Cycle-1 | Validate API response time | Lokesh Prasad | 2026-05-06 | Pass | - | Response time below 2 seconds
TC-API-005 | Cycle-1 | Create note with empty title | Lokesh Prasad | 2026-05-06 | Pass | - | Validation handled correctly
TC-E2E-001 | Cycle-1 | Validate UI-created note in API | Lokesh Prasad | 2026-05-06 | Pass | - | UI and API data matched correctly
TC-E2E-002 | Cycle-1 | Validate API delete reflected in UI | Lokesh Prasad | 2026-05-06 | Pass | - | Deleted note removed from UI successfully

## Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
FR-01 | TC-UI-001, TC-UI-002, TC-UI-003 | User should login successfully and handle invalid login attempts | Covered | Complete
FR-02 | TC-UI-004, TC-UI-006 | User should create notes through UI | Covered | Complete
FR-03 | TC-UI-005 | Newly created note should appear instantly without refresh | Covered | Complete
FR-04 | TC-API-001 | GET /notes API should return notes list successfully | Covered | Complete
FR-05 | TC-E2E-001 | UI-created note should appear correctly in API response | Covered | Complete
FR-06 | TC-API-003, TC-UI-007 | User should delete note successfully using API and UI | Covered | Complete
FR-07 | TC-E2E-002 | Deleted note should disappear from UI after API deletion | Covered | Complete
FR-08 | TC-API-004 | API response time should remain below 2 seconds | Covered | Complete
FR-09 | TC-UI-002, TC-UI-003, TC-API-005 | Application should handle UI and API negative scenarios properly | Covered | Complete

## Defect Report
Defect ID | Test Case ID | Defect Title | Description | Severity | Priority | Status | Assigned To | Reported Date | Remarks
DEF-001 | TC-UI-005 | Delete button click intercepted | Selenium unable to click delete button because another UI element overlaps the button | High | High | Closed | Dev-Team | 2026-05-06 | Fixed using JS scroll and retry click mechanism
DEF-002 | TC-E2E-002 | Deleted note still visible in UI | Note deleted through API still appeared temporarily in UI until refresh | Medium | Medium | Closed | Dev-Team | 2026-05-06 | Resolved after implementing DOM refresh validation
DEF-003 | TC-API-004 | API response delay | GET /notes API response exceeded 2 seconds intermittently | Medium | Medium | In Progress | Backend Team | 2026-05-06 | Performance optimization under analysis
DEF-004 | TC-UI-004 | Multiple note creation instability | Rapid note creation caused intermittent Selenium timing issues | Low | Medium | Closed | Automation Team | 2026-05-06 | Fixed using explicit waits and retry mechanism
DEF-005 | TC-UI-007 | Confirm delete popup delay | Delete confirmation popup occasionally loads slowly | Low | Low | Open | Frontend Team | 2026-05-06 | Requires frontend timing optimization

## Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | UI + API Hybrid Automation – ExpandTesting Notes App
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By: | Chikka Lokesh Prasad
EXECUTION SUMMARY
Total Test Cases: | 14
Test Cases Executed: | 14
Test Cases Passed: | 14
Test Cases Failed: | 0
Pass Percentage: | 100
DEFECT SUMMARY
Total Defects: | 5
Critical Defects: | 0
High Defects: | 1
Medium Defects: | 2
Low Defects: | 2
Open Defects: | 1
Closed Defects: | 4
CONCLUSION
Testing Status: | Completed
Release Readiness: | Ready for Testing Deployment
Overall Recommendation: | Application is stable for QA validation and automation execution.
REMARKS | 1. All UI, API and E2E hybrid test scenarios executed successfully.
2. Selenium framework with Pytest and Requests library integrated successfully.
3. Allure reporting and Jenkins CI pipeline configured successfully.
4. DOM synchronization and API validation functioning correctly.
5. Minor UI timing issues handled using explicit waits and retry mechanisms.